## Rusizi
RUSIZI DISTRICT IMIHIGO FY2022/2023
S/N | Outputs (Under priority area/ sector/ Pillars) | Indicator | Baseline | Source of Data | Targets/milestones |  |  |  |  | Activities and Responsible Institution | Budget (Frw)
[5 empty] | Q1 | Q2 | Q3 | Q4 | Annual Target
ECONOMIC TRANSFORMATION PILLAR
SECTOR: AGRICULTURE
Outcome 1: Agricultural productivity for priority crops increased
1 | Output 1.1: Agricultural productivity through land use management | Number of ha of land consolidated under priority crops | Maize: 9,873 ha | District report |  | 9700 |  | 173 | Maize: 9,873 ha; | DISTRICT, MINAGRI 1. Site Identification of land to be consolidated) 2. Land preparation; 3. Organize meeting of seasons preparations; 5. Train 16,468 Farmers trained through Twigire Muhinzi 6. Planting and Weeding, 7. reporting | 4800000
|  |  | Rice: 2,811ha |  |  | 1455 |  | 1356 | Rice: 2,811 ha
|  |  | Beans: 21,046 |  |  | 8220 |  | 14450 | Beans: 22,670 ha
|  |  | Soybeans: 1,210 ha |  |  | 468 |  | 742 | Soy beans: 1,210 ha;
|  |  | Cassava: 8000 ha |  |  | 8000 |  |  | Cassava: 8,000 ha
2 | Output 1.2: Agricultural productivity through Seeds use increased | Quantity (Kg) of Seeds subsidized bought by farmers | 81,031 kgs of maize used | District report |  | 86353 |  | 4325 | Maize: 90,678 Kg | DISTRICT, 1. Farmer mobilization 2. Follow up the agrodealers to avail input on time 3. Monitor the farmer registration in SNS. 4.Reporting MINAGRI 1. Provide of subsidies | 126905749
|  |  | 3,600 kgs of soybean used |  |  | 4088 |  |  | Soybean: 4,088kg
3 | Output 1.3: Agricultural productivity through fertilizers use increased | Quantity of subsidized fertilizers bought by farmers (Kg) | UREA: 631,754kg | District report |  | 631754 |  | 433673 | UREA: 1,065,427Kgs; | DISTRICT AND MINAGRI 1.Mobilization of farmers, 2. Monitor the distribution of 'Fertilizers via MOPA 3. Reporting, | 632521868
|  |  | DAP: 984.900kg |  |  | 649614 |  | 367914 | DAP: 1,017,528 Kgs;
|  |  | NPK: 711,800 Kg |  |  | 496460 |  | 233861 | NPK: 730,321 Kgs
|  |  | KCl: 392,750 Kg |  |  | 146,393 |  | 254025 | KCL+ Blends: 400,418kgs;
|  |  | MT of lime distributed |  |  | 500 | 1776 |  | 2,276T
4 | Output 1.4: Area of land protected against erosion increased | Number of Ha of progressive terraces constructed | 733.2ha ha progressive terraces | District report | 450 | 0 | 1005 (Cumulative) | 0 | 1005 Ha progressives terraces | DISTRICT 1. Site identification 2. Mobilization of farmers 3. Procurement process 4. Terracing | 130075140
5 |  | Number of Ha of radical terraces constructed | 128.4ha constructed | District report |  | 10 | 20 (Cumulative) | 29 (Cumulative) | 29 Ha of radical terraces |  | 99000000
6 | Output 1.5: Effective and efficient irrigation developed under an Integrated Water Resource Management (IWRM) framework | Number of Ha under Small Scale Irrigation (SSIT) developed | 62,54ha | District report | 7ha | 10ha (Cumulative) | 25ha (Cumulative) | 50ha (Cumulative) | 50ha | DISTRICT, RAB, MINAGRI, COMMUNITY, PSF 1. Farmers Mobilization, 2. Follow up procurement process under RAB 3. training of beneficiaries, 4. Acquisition of irrigation Materials; 5. Irrigation activities; | 108000000
7 | Output 1.6: Insurance of crops provided | Number of Ha of Crops insured | Rice: 2697 Maize:50 | District report |  | Rice: 1348 Maize: 50 |  | Rice: 1349 | Rice: 2697 Maize:50 | DISTRICT 1. Identification of targeted potential farmers to be insured 2. Farmer mobilization 3. linkage of farmers with insurance companies 4. Monitoring and Report into RAB system | 2633527
Outcome 2: Post-harvest infrastructures increased
8 | Output 2.1: Post-harvest drying facilities constructed | Number of drying facilities constructed | 16 | District report |  | Tender process | 40% | 100% | 1 Drying ground constructed in Bweyeye | DISTRICT 1.Identification of Site 2.Tender process 3.Construction of drying ground facility 4. Reporting | 15416230
Outcome 3: Increased animal productivity
9 | Output 3.1: Genetics for cows improved | Number of cows inseminated | 2,374 cows inseminated | District report | 550 | 1200 (Cumulative) | 1850 (Cumulative) | 2477 (Cumulative) | 2,477 Cows inseminated | DISTRICT, RAB, MINAGRI, COMMUNITY 1. Farmer's mobilization, 2. Insemination of cows on natural heat & Insemination on synchronized heat 3. certificate delivery | 6583402
10 |  | Number of AI Carves recorded | 1.006 Calves registered | District report | 172 | 472 (Cumulative) | 772 (Cumulative) | 922 (Cumulative) | 922 cows registered | DISTRICT 1. Identification of calves, 2. Ear tags application, 3. Certificate delivery
11 | Output 3.2: Livestock vaccinated against diseases | Number of domestic animals vaccinated against diseases | 16,016vaccinated against BQ | District report | 8323 | 15323 (Cumulative) |  |  | Domestic animals vaccinated 15,323 BQ | DISTRICT, RAB, MINAGRI, COMMUNITY 1. Farmers' mobilization, acquisition of vaccines, 2. Vaccination of domestic animals | 5050065
|  |  | 16,016 Vaccinated against LSD |  |  |  | 16983 |  | 16,983 LSD
|  |  | 2,508 Vaccinated against Brucellosis |  |  |  | Brucellosis: 2,500 |  | Brucellosis: 2,500
|  |  | Cows vaccinated against RVF |  |  |  |  | Cows: 15,116 | Cows: 15,116
|  |  | Sheep vaccinated against RVF |  |  |  |  | Sheep: 2,273 | Sheep: 2,273
|  |  | Goat vaccinated against RVF |  |  |  |  | Goat: 29,580 | Goat: 29,580
12 | Output 3.3: Insurance of livestock provided | Number of livestock insured |  |  | Pig: 100 Cow: 50 Poultry: 200 | Pig: 109 Cow: 300 Poultry: 500 (Cumulative) | Cow: 600 Poultry: 700 (Cumulative) | Cow: 661 Poultry: 1000 (Cumulative) | Pig: 109 Cow: 661 Poultry: 1000 | DISTRICT 1. Identification of targeted potential farmers to be insured 2. Farmer mobilization 3. linkage of farmers with insurance companies 4. Monitoring and Report into RAB system | 2633527
Outcome 4: Increased cash crops production from 99% to 100% (average growth for both crops)
13 | Output 4.1: Tea production increased | Quantity of dry tea produced (T) | 2,291.922T of made tea produced | District report | 300 | 960 (Cumulative) | 1680 (Cumulative) | 2300 (Cumulative) | 2,300 Tones | DISTRICT, NAEB, MINAGRI, STF 1. Mobilization of tea plucker, 2.Training of Tea pluckers on good practice of plucking 4. Qotary meetings of tea task force 3. Monitoring, reporting. | 6000000
14 | Output 4.2: Coffee production increased | Quantity of Washed Coffee produced (T) | 1,305.161 T | District report |  | Application of mineral fertilizers | 250 | 1350 (Cumulative) | 1,350Tones | DISTRICT, NAEB, MINAGRI, CWS 1. Application of mineral fertilizers 2. Capacity building of coffee farmers through FFS 3. Control of pests and diseases 4. 3 meetings of coffee task force (Q1,Q2,Q3) 5. Monitoring and reporting | 1757294
15 | Output 4.3: Vegetables production increased | Area of vegetables planted (Ha) | 1,025.77 ha | District report | 160 | 400 (Cumulative) | 865 (Cumulative) | 1000 (Cumulative) | 1,000ha | DISTRICT, NAEB, MINAGRI 1. Sensitization of farmers 2. Field preparation 3. Training of farmers on agriculture good practices 4. Monitoring and Reporting | 600000
SECTOR: PRIVATE SECTOR DEVELOPMENT & YOUTH EMPLOYMENT (To include targets for Exports, Tourism and jobs to be created)
Outcome 5: Increased productive Jobs through entrepreneurship and business development
16 | Output 5.1: Productive jobs created | Number of productive jobs created | 46377 | District report | 5,00 | 2,500 (Cumulative) | 4,500 (Cumulative) | 6,000 (Cumulative) | 6,000 Jobs | DISTRICT 1. Identify flagship projects that create jobs, 2. Collect data on the Jobs created from different flagship investment projects, 3. Report on jobs created in flagship projects | 500000
17 | Output 5.2: Start up MSMEs coached to develop bankable projects by Business Development Advisors | Start-up and existing MSMEs (of Youth and women) coached to access finance | 3778 | District report | 25 | 75 (Cumulative) | 125 (Cumulative) | 150 (Cumulative) | 150 start -up MSMEs of youth and women will be coached to access finance | DISTRICT 1. Monitor coaching service rendered by the BDAs and Partners 2. Visit coached beneficiaries projects. 3. Reporting | 3250000
SECTOR: FINANCIAL SECTOR DEVELOPMENT
Outcome 6: Enhanced EJO HEZA Long Term Savings
18 | Output 6.1: Savings increased through Ejo Heza Long Term Saving Scheme | New Savers for Ejo Heza scheme (of which at least 50% are under 30 Years old) | 50338 | District report | 3000 | 8,000 (Cumulative) | 17,000 (Cumulative) | 25,000 (Cumulative) | 25,000 New Savers | DISTRICT 1. Mobilize people to enroll to Ejoheza LTSS 2. Make saving declarations 3. Follow up on savers claims in Ejoheza 4. Reporting MINECOFIN 1. Manage Ejo Heza user friendly system 2. Make payments to savers claims | 10000000
19 |  | Amount of money saved in Ejo Heza | 516,637,428 Frs | District report | 100000000 | 200,000,000 (Cumulative) | 400000000 (Cumulative) | 500000000 (Cumulative) | 500000000
SECTOR: ENERGY (Connections to Productive Use Areas)
Outcome 7: Electricity access to Productive uses areas increased
20 | Output 7.1 Productive use areas connected to electricity | Productive uses areas connected to electricity | 131 connected | District report | 1 | 4 (Cumulative) | 6 (Cumulative) | 8 (Cumulative) | 8 Productive use areas connected to electricity | REG DISTRICT 1. Identification of Productive users, 2. connection of productive use areas, 3. monitoring and evaluation | 200000
SECTOR: URBANIZATION AND RURAL SETTLEMENT
Outcome 8: Accelerate Urbanization to facilitate economic growth
21 | Output 8.1: Urban Infrastructure Developed | completion rate of the implementation of RUDP phase 3 in secondary cities | 10.89 km for RUDP | District report | 10% | 35% (cumulative) | 45% (cumulative) | 60% (cumulative) | 60% (cumulative) | LODA, DISTRICT 1. Procurement process 2. Expropriation 3. relocation of public utilities 4. Construction works, 5. Monitoring and reporting. | 2065623000
22 | Output 8.2: Rural areas connected by suspended bridges | Rate of construction of suspended bridge | MoU signed with B2P |  | 50% | 100% (cumulative) |  |  | 100% of 3 footbridges constructed | DISTRICT 1. Study review 2. Follow up of execution activities 3. Payment | 395263000
SECTOR: ENVIRONMENT AND NATURAL RESOURCES
Outcome 9: Forest coverage maintained and increased
23 | Output 9.1: Area covered by forests increased | Number of Ha of degraded forest Rehabilitated | 265.39ha | District report |  |  | 80 | 90 (Cumulative) | 90ha | DISTRICT, REMA, RF 1.Site identification 2.Mapping 3.Tender process 4.Nurseries establishment 5.Site Preparation 6.Planting 7.Monitoring and Reporting | 23215247
24 | Output 9.2: Area Covered by agroforestry increased | Number of ha of Land planted with Agro forestry | 1,181.7ha | District report |  | 370 | 1293 (Cumulative) | 2052 (Cumulative) | 2052 ha planted | DISTRICT 1.Site identification 2.Mapping 3.Tender process 4.Nurseries establishment 5.Site Preparation 6.Planting 7.Monitoring and Reporting | 49621864
Outcome 10: Fruit trees coverage maintained and increased
25 | Output 10.1: Production of fruits increased | Number of fruit trees distributed to farmers | 824,094 fruits distributed | District report |  |  | 2500 |  | 2,500 fruits distributed | DISTRICT, RAB, TUBURA 1. Identification of farmers 2. Farmers Mobilization 3. Distribution of fruits seedlings 4. Fruits seedlings planting 5. Monitoring and Reporting | 3750000
| Sub Total Budget: ECONOMIC TRANSFORMATION PILLAR | [9 empty] | 3693399913
SOCIAL TRANSFORMATION PILLAR
SECTOR: HEALTH
Outcome 11: Access to health services increased
26 | Output 11.1: Coverage of Community Based Health Insurance Scheme (CBHI) increased | Eligible Population covered under Community Based Health Insurance Scheme (CBHI) | 89.14% | District report | 50% | 90% | 100% | 100% | 100% of the population will be covered in Health Insurance | DISTRICT 1. Mobilization; 2. Payment for vulnerable; 3. Reporting | 1100000
27 | Output 11.2: Access to Health Infrastructure increased | % health centers/posts operationalized | 25 HP are under private operators, 30 work under HC | District report |  | Privatization process | 70% | 100% | 100% | DISTRICT 1. Advertising non operational HP 2. Attribution of HP to the Operators 2. Monitoring HP activities and Reporting
Outcome 12: Maternal, Child and Infant mortality reduced
28 | Output 12.1: Modern contraceptive use increased through Family Planning (FP) services | Prevalence (%) of modern contraceptive use (FP methods) | 88.7% FP Modern contraceptive Utilization rate | HMIS | 53% | 55.5% | 58% | 59% | 59% | DISTRICT 1. Mobilization to the community, mentorship of staff on FP, 2. FP Outreach in Catholic HFs catchment area 3. Supervision of FP service in HFs 4.FP planning coordination meetings | 1000000
29 | Output 12.2: Ante Natal Care (ANC) standard visit attendance increased | 4th Ante Natal Care (ANC) standard visit attendance (%) | 54% | District report | 45% | 46% | 47% | 49% | 49% | District 1. Mobilization in community by CHWs 2. Monitoring and reporting 3. ANC outreach in remote health posts | 1000000
30 | Output 12.3: MCCH services are increased and reinforced in quality delivery and accessibility | Percentage of Births deliveries in health facilities (HC+DH) | 103.8% | District report | 91% | 92% | 93% | 95% | 95% | DISTRICT 1.integrate new 2nd generation health post in HMIS to report deliveries 3.Mobilization 4.Monitoring and reporting | 1000000
31 | Output 12.4: NCDs early detection and management is integrated at community level | People (Aged 35 and above for women; and 40 years and above for Men) who received at least one NCDs community check up within last 12months | 102,534/112,906 screened (90.8%) (2021-2022) | District report | 20% | 55% | 70% | 85% | 85% targets for NCDs community check up (112,906) | MINISANTE/RBC 1. Training of health care providers from health centers and district hospitals on community check up service package DISTRICT 1. Population mobilization and sensitization 2. Follow up of the Program implementation | 1000000
32 | Output 12.5: Covid-19 Vaccination increased | Number of Eligible population (Aged 5-11) to be administered the 1st and 2nd Dose of Covid-19 Vaccine | 0% | District report |  | 40% | 80% | 100% | vaccinate 100% (90522 children 5-11yrs) | DISTRICT 1.Identification of children in nursery and primary schools 2.Requesting vaccines and distribution in Hcs 3. reporting
33 |  | Number of Eligible population (Aged 12 and Above) to be administered the 2nd Dose of Covid-19 Vaccine | 81.07%(228,197/282,207) | District report | 85% | 90% | 95% | 100% | vaccinate 100% 12 yrs missing 2nd dose 28,367 | DISTRICT 1.Counter verification of covid 19 vaccination data 2.Population sanitation 3.Outreach in remote site 4.reportig
34 |  | Number of Eligible population (Aged 18 and Above) to be administered the 1st Booster of Covid-19 Vaccine | 62.4%(176,287/282,207) | District report | 70% | 80% | 90% | 100% | vaccinate 100%(79,921 missing 1 booster) | DISTRICT 1.Counter verification of covid 19 vaccination data 2.Population sensitization 3.Outreach in remote site 4.reportig
35 |  | Number of Eligible population (Aged 59 and Above) to be administered the 2nd Booster of Covid-19 Vaccine | 0% | District report | 10% | 40% | 80% | 100% | vaccinate 100%(20,240 Elders over 59 years | DISTRICT 1.Identificatio of Elders and patient with NCDs 2.Outreach and home vaccination for very old people 3.reporting
FIGHTING MALNUTRITION
Outcome 13: Reduced malnutrition
36 | Output 13.1: Optimal growth for all children under 5 monitored | Under 5 years Children screened for acute malnutrition (MUAC) | 100% | HMIS | 95% | 95% | 95% | 95% | 95% | MoH/CHWs 1. Screening of children District 1. Sensitize parents 2. Screening site supervision | 4065040
37 | Output 13.2: Stunting reduced among Children under 2 | Percentage children aged 3,6,9,12,15 and 18 Months screened using length mat for stunting visualization | 100% | NECDP reports | 35% | 70% | 90% | 95% | 95% | MoH/CHWs 1. Avail equipment 2. Screening of children District 1. Mobilize parents 2. Follow up with health centers to ensure growth monitoring is done 3. Distribution of length mate
38 | Output 13.3: Home Based ECDs operationalized in all Villages | Percentage of children 3-6 years per Village attending ECD facilities/settings (home, community, center based) | 80% | District report | 65% | 80% | 90% | 95% | 95% | District: 1. Organize training on ECD services 2. Identification of beneficiaries 3. Distribution of food and porridge 4. Monitoring and reporting | 103540000
39 |  | Percentage of parents with children aged 0-35months benefiting from early child stimulation and positive parenting services through home visitations by CHWs | 85% | District report | 55% | 65% | 75% | 85% | 85% | District: 1. Organize training of CHWs on ECD services 2. Identification of beneficiaries 4. Monitoring and reporting
40 |  | '% of ECD settings meet the minimum quality standards for accreditation | 63% | District report | 45% | 50% | 60% | 65% | 65% | District: 1. ECDs need assessment to meet quality standards 2.Certification of ECDs meeting quality standards 3. Distribution of Materials 4. Monitoring and reporting | 12000000
SECTOR: EDUCATION
Outcome 14: All schools, TVET and higher education institutions have sufficient modern infrastructure, facilities and resources
41 | Output 14.1: New classrooms constructed | Construction of 16 new Classrooms and 18 new latrines |  | District report | 10% | 40% | 40% | 10% | 100% | District 1.Site identification and site confirmation 2 Construction works, 3. Official inauguration | 168233614
42 | Output 14.2: New ECDs constructed | Rate of completion of ECD constructed | 5% | District report | 98% | 100% |  |  | 2 ECDs constructed at 100% | District & AEE 1.Construction works, 2.Equip ECDs 2. Official inauguration | 90000000
Outcome 15: Enhanced the quality of education through improved teacher's welfare and schools operations
43 | Output 15.1: Timely payment and management of school grants | Payments for Teachers’ salaries made on time (Submission of payment requests not later than 15th of every Month) | 91.6% | District Reports | 100% | 100% | 100% | 100% | 100% of Payments of Teachers' salaries made on time Payment request submitted to MINECOFIN not later than 15th of every Month | District: 1. Prepare payroll lists 2. Submission of Payment request to MINECOFIN not later than 15th of every Month MINEDUC: 1. Approval of Teachers placement 2. Verification and approval of payment lists not later than 17th of every month 2. Monitoring and follow up on timeliness of payment of teachers' salaries MINECOFIN: 1. Verify and process teachers' salaries not later than 20th of every month | N/A
44 | Output 15.2: Timely payment and management of school grants | Payments for Capitation grant and School Feeding ) based on MINEDUC Authorization | 100% | District Reports | 100% | 100% | 100% | 100% | 100% | DISTRICT 1. Prepare lists of schools benefiting the capitation Grant through SDMS 2. Verify and approve the lists of schools that benefit from capitation grant and submit to MINECOFIN 3. Prepare payment orders after approval of the lists and submit to MINECOFIN (within 3 weeks of the first month of academic term) MINEDUC 1. To prepare and issue to districts guidelines for the use of Capitation Grant 2. To monitor the use of capitation grant | N/A
Outcome 16: All students in primary, secondary school and TVETs complete the year of learning
45 | Output 16.1: All Learners attended schools on regular basis | Percentage of students attending school (Primary, Secondary and TVETs) | Attendance in Primary 100416/101956=98.4% Attendance in Secondary 25368/25096= 101%, Attendance in TVET: 3092/3120=99.1% | SDMS | 95% | 97% | 98%% | 98%% | 98% at all levels | District: 1. Inspect schools and give the recommendations 2. Report on primary, secondary and TVET school attendance 3. Mobilize parents 4. Provide lunch to Nursery, Primary nd Secondary school students through School feeding program 5. Proper use of class register (Ibidanago) MINEDUC 1. Monitor reporting of Education statistics | 6000000
46 |  | Number of students enrolled in preprimary schools | Pre-primary: 100% | report from SDMS | 96% | 98% | 100% | 100% | 100% of 12,800 Students enrolled in preprimary schools | District: 1. Inspect schools and implement the recommendations 2. Identify children of pre-primary school age who are out of schools 3. Report on primary, secondary and TVET school enrolment, attendance and completion rates 4. Mobilize parents in holydays 7.MINEDUC 1. Monitor reporting of Education statistics
Outcome 17: Strengthening national administrative data: Civil Registration and vital statistics and Education administrative Statistics
47 | Output 17.1: Education administrative statistics collected and timely registered through School Data Management System (SDMS): Primary Secondary and TVETs | Education information recorded into the SDMS system with accuracy | Currently 100% of information on students are in to SDMS | SDMS | 100% | 100% | 100% | 100% | 100% | MINEDUC/ DISTRICT 1. Provide technical support to schools /sector and district 2.Capacity building on the use of SDMS 3. Monitoring the use of the SDMS DISTRICT 1. Ensure that all schools are recorded in to the system 2. Measures for re-enrollment of dropped out students and strategy to ensure that they will complete the level. 3. Identification of dropped out students 4. Effectively record students and monitor school attendance rate for students and teachers, | N/A
Outcome 18: Improved performance of students in annual assessments and national examinations.
48 | Output 18.1: Students performance (Lower Primary, Secondary and TVET) increased | Percentage of Students passing comprehensive assessment: Primary, Secondary, and TVET L3 to 5 | Primary:44.8% Secondary; 45.7% TVET: 62.1%% | REB Reports | Primary:45% Secondary; 46% TVET: 63% | Primary:45% Secondary; 46% TVET: 63% | Primary:45% Secondary; 46% TVET: 63% |  | Primary:45% Secondary; 46% TVET: 63% | MINEDUC 1. Analysis of national examinations results. 2. dissemination of analysis report at districts level DISTRICTS 1. Self assessment of national exam performance 2. Conduct and keep record of continuous/ formative assessments term 2 3. Analysis/Self assessment of comprehensive assessment term 1 and term 2 4. Monitoring and reporting | N/A
Outcome 19: Increased access to adult literacy
49 | Output 19.1: Adult literacy and numeracy increased | Number of people trained in adult literacy centers | 2733 | District report | Mobilization and site identification (20%) | Teaching Period , and training for trainees ( 40%) | Monitor teaching period ( 80) | Passing Exams, graduate and award with certificate (100%) | 3000 adult people will graduate from adult literacy scheme | DISTRICT 1. Identification people to be trained, 2. Training for trainees 3. Monitor teaching process, 4. Assessment and issuance of certificates | 12837213
SECTOR: SOCIAL PROTECTION
Outcome 20: Increased coverage and delivery of core Social protection programs
50 | Output 20.2: Labor intensive cPW and ePW delivered to extremely poor households | Number of eligible HHs benefiting from Classic Public Works (cPWs) | 1,930 HH (2021-2022) | District report |  | 3,525HHs | 3,525HHs | 3,525HHs | 3,525HHs | DISTRICT 1. Procurement of Public works projects 2. follow up execution of PW projects | 332618242
51 |  | Number of eligible HHs benefiting from Expanded Public Works (ePWs) | 909HHs (2021-2022) | District report |  | 1,562 HHs | 1,562 HHs | 1,562 HHs | 1,562 HHs | DISTRICT 1. Procurement of Public works projects 2. follow up execution of PW projects
52 | Output 20.3: Payments to VUP beneficiaries delivered on time | Timely payments made to VUP beneficiaries (DS: within 10 days after the end of the month and ePWs&cPWs: within 15 days after the end of working period) | 100% | District report | 100% | 100% | 100% | 100% | 100% of payments (DS: within 10 days after the end of the month and ePWs&cPWs: within 15 days after the end of working period) | District 1. Pay check lists 2. Pay beneficiaries on time and regularly 3. Timely submission of OPs to MINECOFIN (DS: by 15th Day of the month)
53 | Output 20.4: Eligible beneficiaries supported through Financial services | Loans advanced to eligible beneficiaries under VUP/Financial services to support their Income Generating Activities | 4,506 loan advanced | District report | 800 | 1,500 (Cumulative) | 1,800 (Cumulative) | 2,000 (Cumulative) | 2,000 loans advanced to eligible beneficiaries under VUP/Financial services | DISTRICT: 1. Mobilize VUP-FS beneficiaries to access loans 2. Monitor loans disbursement activities 3. Make field visit to financed projects 4. Make loan recovery mobilization 5. Follow up of funds management under Financial Services 6. Reporting | 1000000
54 |  | Repayment rate of loans provided through VUP financial service third scheme loans recovered | 77.9% | District report | 70% | 75% | 78% | 80% | 80% of repayment rate on VUP financial service third scheme loan |  | 1000000
Outcome 21: Vulnerable poor households have increased access to complementary livelihood to enhance their economic empowerment through multi-sectorial approach implementation
55 | Output 21.1: Poor families are supported with cows through Girinka program | Number of poor families who received cows through Girinka program | 9,687 Families received cows | District report | 100 | 400 (Cumulative) | 650 (Cumulative) | 881 (Cumulative) | 881 Families supported with cows | DISTRICT: 1. Validation of beneficiaries list, 2. Training of beneficiaries, 3. Tender process of cows to be purchased, 4. Distribution of heifers through pass and purchased cows 5. Monitoring and reporting | 110500000
56 | Output 21.2: Multi- sectoral approach implemented to enhance graduation of vulnerable Households out extreme poverty | Number of extremely poor HHs supported through Multi- sectoral Social protection to Vulnerable HHs in Ubudehe Cat.1 | 1009 | LODA MEIS |  |  | 1) 70 Vulnerable HHs in Ubudehe Cat.1 supported with assets transfer 2) 210 Vulnerable HHs with Small Livestock 3) 150 Children from Vulnerable HHs in Ubudehe Cat.1 supported to enroll in schools 4) 86 People supported to access technical/ vocational skills 5. 60 Vulnerable HHs supported with Off grid energy | Monitoring and follow-up | 576 HHs supported through Social protection to achieve minimum required livelihoods | District: 1. Identification of beneficiaries 2. Mobilization of the stakeholders 3. Give support, monitoring and reporting | 11145000
57 | Output 21.3: Poor families are supported with Small livestock | Number of Small Livestock Distributed (Poultry-Sasso and Layers and Pigs) | 38,138 Poultry, 1,119Pigs | District report |  |  | Distribution of 4,000 Poultry and 40 Poultry | Distribution of 5.000 Poultry and 140 pigs (Cumulative) | Distribution of 140 Pigs and 5000 Poultry | DISTRICT 1. Identification of beneficiaries 2. Tender process 3. Training of beneficiaries 4. Distribution 5. Mobilization of Partners 6. Follow-up and reporting MINAGRI 1. Providing guidelines 2. Technical support 3. Provide resources | 140160000
58 | Output 21.4: Genocide survivors provided with adequate shelter | Number of houses constructed for eligible Genocide Survivors | 263 | District report | Identification of beneficiaries, site identification, expropriation (10%) | 20% 1. Terracing, 2. Foundation works | 50% Elevation works (Roof fixing) | 100% Finishing works and provisional hand over | 70 houses constructed at 100% | DISTRICT 1. Identification of beneficiaries and sites 2. Tender process 3. Follow up of construction activities 4. Payment 5. Provisional handover 6. Offering houses to beneficiaries | 1076000000
59 | Output 21.5: Direct support provided to needy genocide survivors | % of needy genocide survivors provided Ordinary Direct Support within 10 days following the end of the month |  | District reports | 100% | 100% | 100% | 100% | 100% | District 1. Pay check lists 2. Pay beneficiaries on time 3. Timely submission of OPs to MINECOFIN (DS: by 15th Day of the month) | 245250000
60 |  | % of needy genocide survivors provided Special Direct Support within 10 days following the end of the month |  | District reports | 100% | 100% | 100% | 100% | 100% |  | 23400000
61 |  | Number of needy genocide survivors provided with Minimum Package Support |  | District reports |  |  |  | 75 | 75 | DISTRICT 1.Identification of beneficiaries 2. Provide support 3. Monitoring and reporting MINUBUMWE 1. Provide guidelines and Budget | 33750000
62 |  | Number of needy genocide survivors provided support for Income Generating Activities |  | District reports |  |  |  | 150 | 150 | DISTRICT 1.Identification of beneficiaries 2. Provide support 3. Monitoring and reporting MINUBUMWE 1. Provide guidelines and Budget | 75000000
63 | Output 21.6: Direct support provided to needy Genocide Survivors | Timely payment of DS (special and ordinary) within 10 days following the end of the month | 1903 | District Report | 100% | 100% | 100% | 100% | 100% | DISTRICT & FARG 1. Identification of beneficiaries 2. Timely submission of OPs to MINECOFIN (DS: by 10th Day of the month) 3.Pay beneficiaries on time and regularly
64 | Output 21.7: People with disabilities empowered | Number of PwDs Cooperatives financially supported | 4 (2021-2022) | District report |  |  | 2 cooperatives | 2 cooperatives | 4 Cooperatives supported | DISTRICT: 1) Projects analysis 2) Fund disbursement 3) Projects monitoring NCPD 1. Budget disbursement | 4000000
65 | Output 21.8: Disability Mainstreaming | Number of PWDs supported with assistive devices | 125 (2021-2022) | District report |  |  | 60 | 125 (Cumulative) | 125 | DISTRICT: 1) identification of beneficiaries 2) Stakeholders mobilization 3) monitoring and reporting NCPD 1. Budget disbursement | 3000000
GENDER AND FAMILY PROMOTION
Outcome 22: Family cohesion strengthened
66 | Output 22.1: Umugoroba w'Ababyeyi promoted at Village level | Percentage of villages in the district with operational Umugoroba w'Imiryango | Quarterly inspection | District Report | 100% | 100% | 100% | 100% | 100% | District 1. Distribution of guidelines, 2. Organize Quarterly team of inspection, 3. Make Quarterly inspection in all village | 5192308
67 | Output 22.2 Child protection increased | Proportion of teenage mothers who reintegrated to school | 34.4% | District Report |  | Stakeholders mobilization | 10'% | 25% | 25% of identified | District 1. Identification of beneficiaries 2. Stakeholders mobilization 3. Enrolled to schools 4. Reporting
68 |  | Percentage of identified child protection cases from July 2022 to March 2023 handled by District (Cases from IZU, 711 hotline and other channels) |  | District Report | 80% | 80% | 80% | 80% | 80% | District 1. Identification of beneficiaries 2. Quarterly meeting with IZU 3.Trainings of Foster Cares. 4. Provide Financial and Psychosocial support to Children in need 5.Numbers of Cases handed and Reported | 5000000
69 | Output 22.3: Child Labour Elimination | Level of operationalization of Child Labour Elimination and Prevention Committee at District, Sector, Cell and Village level | Child Labour Elimination and Prevention Committee is operational at District, Sectors, Cells, and Villages at 100% | MIFOTRA administrative data | 100% | 100% | 100% | 100% | Child Labour Elimination and Prevention Committees operationalized at 100% | DISTRICT: 1.Conduct at least 3 inspections on elimination and prevention of child labour on quarterly basis by each committee at all levels(District,Sector,Cell and Village); 2.Conduct at least 3 awareness campaigns on elimination and prevention of child labour on quarterly basis by each committee at all levels (District,Sector,Cell and Village); 3.Record the number of children which were removed from child labour and reintegrated into families and in schools; 4. Report to RIB employers and other people who engage children in child labour related matters for law enforcement; 5. Conduct at least 3 child labour elimination and prevention committee's meetings at all level ( District,Sector,Cell and Village) | 2000000
Outcome 23: Delinquency prevented through rehabilitation and reintegration of former Delinquents
70 | Output 23.1: Reintegration of former street Children and delinquents | Percentage of former delinquents from rehabilitation centers reintegrated (continued education, self-employed or employed) | 37 in 2021/2022 | District report |  | 10% | 70% | 90% | 90% | District 1. Identification of beneficiaries, 2. Conduct meeting with stakeholders 3. Reintegration and support youth from rehabilitation centers | 3000000
71 |  | Percentage of identified street children reunified with families | 100% | District report | 100% | 100% | 100% | 100% | 100% | District 1. Identification of street children, 2. Conduct meeting with stakeholders 3. Reunify street children with families
Outcome 24: Increased household access to Electricity
72 | Output 24.1: Access to electricity increased | Number of New households connected to on-grid electricity | 48,858 HHs connected | District activity report | 500 HHs | 1500 HHs (Cumulative) | 3500 HHs (Cumulative) | 5000 HHs (Cumulative) | 5,000HHs will be connected | DISTRICT 1. Identification of potential beneficiaries; 2. Mobilization; 3. Connection of hhs 4. Monitoring & reporting | 500000
73 | Output 24.2: Access to renewable energy increased | HHs mobilized and acquired Improved Cook Stoves | 1,935 HHs | District activity report |  | 500 | 1,200 (Cumulative) | 2,000 (Cumulative) | 2,000 HHs | DISTRICT 1. Identification of potential beneficiaries; 2. Linkage of Suppliers and Communities through mobilization Meetings 3. Acquisition of cooking stoves 4. Monitoring and Reporting
SECTOR: WATER AND SANITATION
Outcome 25: Increased access to clean drinking water
74 | Output 25.1: Households with access to water infrastructure increased | New households connected to safe/drinking water (into their dwellings/premises) | 79,352 HHs access to water | District report | 180HHs | 300 HHs (cumulative) | 500 HHS (cumulative) | 700 HHs (cumulative) | 700 HHs | WASAC and DISTRICT 1. Identification of potential beneficiaries; 2. Make connections; 3. Monitoring; Reporting | 500000
75 | Output 25.2: Access to Water increased | New Public institutions and socio-economic use areas connected to clean water | 202 Public institutions and social economic use areas connected to clean water | District report |  | 2 | 5 (cumulative) | 10 (cumulative) | 10 | WASAC and DISTRICT 1. Identification of Public institutions and socio-economic use areas to be connected 2. Make connections; 3. Monitoring; Reporting
76 | Output 25.3: Water Supply Systems in good condition (Water Network) | Percentage of completion of Water Supply System constructed (KM-Water Network) | 945 km | District Activities report | 25% | 80% | 100% |  | 100% (30 km) | WASAC and DISTRICT 1. Study review, 2. Construction works, 3. Monitoring & Supervision, reporting 5. Provisional acceptance | 2000000
77 |  | Percentage of completion of Water Supply System rehabilitated (Km-Water Network) | 75.5km | District Activities report | 25% | 80% | 100% |  | 100 % (7 km) | WASAC and DISTRICT 1. Study Review, 2. Construction works, 3. Monitoring & Supervision, reporting 4. Provisional acceptance | 2000000
78 | Output 25.4: Public water taps operationalized and properly managed | Percentage of operational public water taps on functional Water Supply Systems | 95.2% | District report | _ | 100% | 100% | 100% | 100% Operational of water taps | District 1. Identification of non-operational water taps 2. Meeting with WASAC, DISTRICT and Private operator 3. Organize wash steering committee meetings 4. Rehabilitation of non operational water taps 5. Monitor and reporting | 15000000
SECTOR: URBANIZATION AND RURAL SETTLEMENT (Social Aspects)
Outcome 26: Increased access to improved settlement
79 | Output 26.1: Increased access to improved settlement | Number of HHs living in High risk zone relocated | 160 | District report | 2 HHs | 12 HHs (Cumulative target) | 30 HHs (Cumulative target) | 42HHs (Cumulative target) | 42HHs (cumulative) | DISTRICT 1. Identification of hhs to be relocated; 2. Mobilization of Identified hhs; 3. Relocation of hhs from HRZ to Planned site settlement, 4. Monitoring, Reporting | 2100000
Outcome: Management of IDP Model Villages improved
80 | Output: Management issues in IDP Model villages resolved | % of identified issues in IDP Model Village resolved | IDP Model village Issues identified by different stakeholders | Districts Quarterly Report | 1) Assessment on IDP Model Village issues conducted; 2)Implementation plan to JOINTLY address identified issues elaborated | 20% | 50% | 80% | 80% | MINALOC: 1) Coordinate the operationalization of the IDP Technical Committees at District level; 2) Establish Sector level IDP Technical committees; 3) Conduct quarterly CG-LG Engagement Meetings on IDP Management 4) Conduct inspection on management of IDP Model villages Districts 1) Conduct quarterly assessment to identify issues in respective IDP Model Villages 2) Elaborate an implementation plan to address issues identified 3) Implement recommendations of assessments on Issues in IDP Model Villages 4) Provide capacity building to IDP beneficiaries on proper management 5) Organize engagement sessions with stakeholders in search for solutions to issues identified 6) Operationalize the District and Sector IDP Technical Committees 7) Appoint staff in charge of regular follow up on the IDP Model Villages Management
HUMAN SECURITY ISSUES
Outcome 27: Human Security issues addressed
81 | Output 27.1 Human security issues addressed through construction and rehabilitation of shelters and toilets for vulnerable households | Number of houses for eligible vulnerable households constructed | 721 houses constructed | District report |  | 250 |  |  | 250 houses to be Constructed | DISTRICT: 1. Mobilization of community to participate in community works to construct shelters of Vulnerable Households; 2. Distribution of Materials 3. Monitoring and reporting MINALOC: 1. Monitor mechanisms to address HSI in LGs 2. Support in resources mobilization | 136250000
82 |  | Number of houses for eligible vulnerable households rehabilitated | 3,452 houses rehabilitated | District report |  | Sites Visit and Mobilization of Resources | 900 | 1,500 (Cumulative) | 1,500 Houses to be rehabilitated | DISTRICT: 1. Mobilization of community to participate in community works to rehabilitate shelters of Vulnerable Households; 2. Distribution of Materials 3. Monitoring and reporting MINALOC: 1. Monitor mechanisms to address HSI in LGs 2. Support in resources mobilization | 75000000
83 |  | Number of toilets for eligible vulnerable households constructed | 1993 Toilets constructed | District report |  | 96 |  |  | 96Toilets to be constructed | DISTRICT: 1. Mobilize HHs to construct toilets MINALOC: 1. Monitor mechanisms to address Human security Issues in LGs 2. Support in resources mobilization | 750000
84 |  | Number of toilets in poor condition rehabilitated for vulnerable households | 6,767 Toilets rehabilitated | District report | 180 | 1980 (Cumulative) | 2160 (Cumulative) | 3620 (Cumulative) | 3620 Toilets to be rehabilitated | DISTRICT: 1. Mobilize HHs to rehabilitate toilets in poor conditions MINALOC: 1. Monitor mechanisms to address Human security Issues in LGs 2. Support in resources mobilization | 8000000
| Sub Total Budget: SOCIAL TRANSFORMATION PILLAR | [9 empty] | 2625891417
TRANSFORMATIONAL GOVERNANCE PILLAR
GOVERNANCE AND DECENTRALIZATION AND TRANSFORMATIONAL LEADERSHIP
Outcome 28: Improved governance, service delivery and accountability in Local Government
85 | Output 28.1: Citizens demands/complaints received and timely resolved by Local Government | % of Citizens' demands/complaints received and timely resolved by Local Government | 95.2% | District report | 45% | 60% | 75% | 95% | 95% | District 1. Receive and resolve all citizen complaints 2. Share complaints information via e-citizen system and provide a feedback 3. Monitoring and Reporting | 600000
86 | Output 28.2: Local Government Capacity Development increased | Percentage of Local Government staff and elected leaders benefited from capacity development interventions (disaggregated by Sector, Cell and Village) |  | District report | 50% | 50% |  |  | 100% | DISTRICT, RALGA, MINALOC 1) Training of trainers 2) Training of Local government and elected Leaders 3) Monitoring and reporting
87 | Output 28.3: Quality service delivery institutionalized | Percentage of Irembo services delivered by Local Government within the set timeframe | 99.63% | Irembo Reports | 95% | 95% | 95% | 95% | 95% | 1. Process and deliver requested services 2. Mobilize citizens on Irembo services 3. Reporting | N/A
88 |  | Number of assessments hierarchically conducted on sub District entities performance in transformational imihigo | 3 assessment conducted | District report |  | First assessment | Second assessment | Third assessment | 3 Assessments hierarchically conducted | District 1.Evaluation format elaboration 2. Conduct assessment 3. Certificates Awarding to Sectors 4. Monitoring and Reporting | 4000000
89 | Output 28.4: Modernized civil registration and systems integration for online authentication strengthened. | Percentage of birth and death events occurring at health facilities timely recorded in NCI-CRVS | Birth: 96% Death: 67.2% | District report | Birth: 97% Death: 97% | Birth: 97% Death: 97% | Birth: 97% Death: 97% | Birth: 97% Death: 97% | Birth: 97% Death: 97% | District '1. Sensitization meetings; 2. Compile electronically the civil registration vital statistics per administrative entity; 3. Monitor the electronically the civil registration vital statistics; 4. Reporting | 500000
90 |  | Percentage of marriage and divorce events timely recorded in NCI-CRVS | Mariage:100% Divorce: 100% | District report | Marriage: 100% Divorce: 100% | Marriage: 100% Divorce: 100% | Marriage: 100% Divorce: 100% | Marriage: 100% Divorce: 100% | Marriage: 100% Divorce: 100% | District 1. Sensitization meetings; 2. Compile electronically the civil registration vital statistics per administrative entity; 3. Monitor the electronically the civil registration vital statistics; 4. Reporting | 500000
91 |  | Percentage of births and deaths occurring at community timely registered in the NCI-CRVS system |  | District report | 97% | 97% | 97% | 97% | 97% | District 1. Sensitization meetings; 2. Compile electronically the civil registration vital statistics per administrative entity; 3. Monitor the electronically the civil registration vital statistics; 4. Reporting | 500000
OUTCOME 29: Reinforced marriage for families cohesion and relations
92 | Output 29.1: Marriage documents well maintained | Percentage of identified illegal marriage legalized |  | District report | 60% | 60% | 60% | 60% | 60% | DISTRICT 1) Citizen mobilization 2) Identification of illegal marriage 3) Illegal marriage legalized
Outcome 30: National Values, Ethics and National Service Promoted.
93 | Output 30.1: Itorero and National service program implemented | '% of primary and secondary schools in which Itorero is operational | 100% | District report |  | Organize and refresh Itorero Schools trainers | Conduct one session dialogue to each School | Conduct one session dialogue to each School | 100% | DISTRICT 1. Conduct training, 2. Reporting | 10000000
94 |  | % of Villages in which Itorero is effectively operational in line with its mission | 100% | Districts reports |  | Organize and refresh Itorero trainers | Identification of students dropout and enrolled to schools | Preparation of 5 kitchen garden at each villages | 100% | DISTRICT 1.Organize and refresh Itorero Ry'Umudugudu trainers 2. Identification of beneficiaries 3. Monitor and report the operationalization of Itorero | 8075800
95 |  | Proportion of youth ( S.6 finalist) enrolled in Voluntary National Service (Urugerero) |  | Districts reports |  |  |  | 75% | 75% | DISTRICT 1.Organize and refresh Itorero trainers 2. Identification of beneficiaries 3. Monitor and report the operationalization of Itorero
96 | Output 30.2 Functional-Ndi Umunyarwanda dialogue spaces within different groups of people events conducted | No. of Sectors that conducted Ndi Umunyarwanda dialogues among None Schooling Youth | 18 Sectors | Districts reports |  | 18 |  |  | 18 Sectors | District 1. Identification of the participants by categories 2. Identification of Sites, 3. logistics preparation 4. Training 5. Monitoring and reporting | 3025000
97 |  | % of primary and secondary head teachers attend Ndimunyarwanda dialogues | 100% | Districts reports |  | 100% |  |  | 100%
SECTOR: JUSTICE RECONCILIATION LAW AND ORDER
Outcome 31: Improved access to quality Justice
98 | Output 31.1 Justice delivery at local level reinforced | % of Judgments received before 01/04/2023 executed | 100% | District report | 10% | 30% | 60% | 85% | 85% | District 1. Identification of judgments that are to be executed ; 2. Execution of judgements; 3. Monitoring and Reporting | 500000
99 |  | % of cases received from 1st July 2022 to 30 April 2023 settled by mediation committees "Abunzi" | 98.8% | District report | 20% | 40% | 70% | 98% | 98% | District 1. Receiving complaint, 2. Organize the session to settle the cases 3. Monitoring and Reporting | 11655000
SECTOR: PUBLIC FINANCE MANAGEMENT
Outcome 32: Increased district own revenues generation capacity
100 | Output 32.1 District Own revenues increased | Amount of District own revenues generated (Frw) | 2,491,813,849 | District report | 508,145,435 (Cumulative) | 1,293,847,528 (Cumulative) | 2,302,783,673 (Cumulative) | 2,830,600,127 (Cumulative) | 2830600127 | DISTRICT and RRA 1. Identification of taxpayers, 2. Sensitization on tax payment, 3. Collection of taxes | 222499654
Outcome 33: Increased transparency and accountability of Public funds in Local Government
101 | Output 33.1: Public accountability enhanced and PFM strengthened | Auditor General's Recommendations implemented | OAG recommendation implemented at 63 % in 2021-2022 | District report | 20% | 40% | 60% | 80% | 80% | DISTRICT 1. Monitor implementation of the Auditor General's recommendations | 2000000
102 | Output 33.2: Public funds recovered from won cases | Percentage of Government funds recovered from recoverable won cases | 30.9% | District report |  | 20% | 50% | 85% of recoverable won cases | 85% (31,172,996) | DISTRICT 1. Purchasing of judgment copies 2. Identification of recoverable government funds in RUSIZI District, 3. monitoring and reporting | 2000000
103 | Output 33.3: NBAs audited in line with PFM | Percentage of NBAs audited (by Internal Auditors) in line with PFM | Audit 39 NBAs in 2021/2022 | District report |  | 8% | 20% | 25% (Cumulative) | 25% (39 NBAs) | DISTRICT: 1. Develop audit plan; 2. Conduct audit to 25% of District NBAs | 2000000
104 | Output 33.4: District NBAs assessed through peer review-peer learning approach | Percentage District NBAs assessed using peer review-peer learning approach | 100% | District report |  | 50% | _ | 100% | 100% | DISTRICT: 1. Identification of NBAs to be assessed 2. Conduct joint assessment of NBAs 3. Monitoring of implementation of peer review-peer learning recommendations
| Sub Total Budget: TRANSFORMATIONAL GOVERNANCE PILLAR | [9 empty] | 267855454
| TOTAL BUDGET: | [9 empty] | 6587146784